Development of nutritional guidelines and training of health workers on nutrition and HIV/AIDS

# INTRODUCTION TO THE PROBLEM

Healthy nutrition is important for everybody, especially for people living with HIV/AIDS (PLWHA’s). Healthy eating means eating a variety of foods providing an appropriate amount of energy and nutrients for the body. The body’s needs for energy and nutrients increases in case of sickness. Therefore, PLWHA’s need to pay extra attention to their diet in order to keep their weight at a proper level and to help strengthen the body and fight against infection.

For the majority of PLWHA’s including AIDS orphans in Ghana, it is not possible to eat an appropriate diet that would prevent weight loss and strengthen their immune system. They are faced with different kind of problems, which makes eating difficult. These problems include reduced food intake caused by their medical condition (lack of appetite, nausea and vomiting, diarrhea, fungal infections etc.), poverty, stigmatization and inadequate information on nutrition in relation to HIV/AIDS.

Nutritional support adjusted to the nutritional, medical, financial and socio-cultural situation can help prevent weight loss, improve well being and contribute to the quality of life.

# THE AIM OF THE PROJECT

The development of a nutritional guideline specifically for (marginalized) people living with HIV/AIDS in (the three Northern Regions of) Ghana adjusted to their nutritional, medical, economical and socio-cultural situation. This would be followed by the training of PLWHA’s, their caregivers and particularly health workers on the use of the nutritional guidelines as part of the treatment of PLWHA’s and AIDS orphans.

THE OBJECTIVES OF THE PROJECT

1.	To come out with cost-effective healthy diet according to the requirements for

PLWHA’s in Ghana

2. 	To come out with practical dietary advises for the food related complaints caused by the disease (weight loss, lack of appetite, nausea and vomiting, diarrhea, fungal infections etc.)

3.	To analyze the composition of local food items and to examine the benefits of these items on the nutritional status of PLWHA’s

4.	To inquire the economical and socio-cultural situation of PLWHA’s in especially the three Northern Regions of Ghana

5. 	To develop a guideline for nutritional treatment for PLWHA’s in Ghana (especially the three Northern Regions) based on objective 1, 2, 3 and 4.

6.	To educate health workers on the importance and the content of nutritional support as part of the treatment and care of PLWHA’s including malnourished AIDS orphans.

7.	To educate PLWHA’s and their care givers on the content of a healthy diet in relation to HIV/AIDS

# PLAN OF ACTIVITIES AND TIME SCHEDULE

1.	Development of the draft guideline based on	          januari – februari 2004

- Information obtained from the pre survey period (August/December 2003):

-     Theoretical research on Ghanaian food pattern, eating habits and nutrition in

relation to HIV/AIDS

- Finding from dietary consultations of PLWHA’s at the out and in patient department of the International Health Care Centre in Accra and home visits

- Interviews with key informants

- Observations and interviews during visits to the Upper West Region

2.	Organizing a focus group discussion				 februari 2004

- Solicit feedback on the content of the draft guideline from community members and key informants and adapt the draft to their suggestions

Dissemination workshop

- Evaluation of the draft guideline with stakeholders

3.  	Trial period 						                 march – june 2004

- Guideline will be put into practice during a four months trial in Wa, Lawra and Nandom in the Upper West Region among the members of the three associations for PLWHA’s (Shalome 1, Shalome 2, Shalome 3)

- 	group meetings on monthly basis for shalome 1,2, and 3

  - individual dietary counseling for twenty ( 15 adults / 5 children) members of  shalome 1 every two weeks and monitoring the changes in nutritional and medical status

-	individual dietary counseling for ten members of shalome 2  (7 adults / 3 children) once a month and monitoring the changes in nutritional and medical status

-	individual dietary counseling for ten members of shalome 3 (7 adults / 3 children) once a month and monitoring the changes in nutritional and medical status

- Interviews and observation of food preparation and the socio-cultural norms during home visits.

In total twelve home visits will be done; eight members of shalome 1, two members of shalome 2 and two members of shalome 3

- Visits to the market of Wa, Lawra and Nandom and observe the availability of the various food items and to analyze the content and the cost.

- Interviews with key informants

# 4.  	Development of the final version of the guideline based on:	         july 2004

- Findings of the trial period

- Additional information given by literature and key informants

### Development of a training schedule for activity 6 and 7

# 5.  	Publishing the guideline				          august-september 2004

- Designing the lay-out of the guideline

- Producing the cost-effective guideline

# 6.  	Training of  health workers of care and treatment facilities          october 2004

- Organizing training workshops for health workers of care and treatment facilities for PLWHA’s and AIDS orphans on the importance of nutritional support and the implementation of the guideline.

In total four training workshop will be given; one in the Upper West, one in the Upper East, one in the Northern Region and one in Greater Accra. Each workshop consists of three training days.

7. 	Training of PLWHA’s and their care givers		           november 2004

- Organizing a training on healthy nutrition and HIV/AIDS for PLWHA’s

and their care givers according to the content of the guideline.

In total nine trainings will be given, three trainings in the Upper West, three in the Upper East, three in the Northern, and three in the Greater Accra regions.

Supervision of the implementation of the guideline by health workers

- Visiting health care facilities for PLWHA’s and AIDS orphans and supervise the use of the guidelines by the health workers.

In total nine health care facilities will be visited; three locations in the Upper West, three locations in the Upper East, three locations in the Northern Region while three locations will be in the Greater Accra region.

8. 	Final release of the guideline to public			           december 2004

OVERVIEW OF THE EXPECTED INDEX OF THE GUIDELINE

Introduction

Nutrition and HIV/AIDS

Composition of a healthy diet

Prevention and treatment of weight loss

Loss of appetite

Sore mouth and throat

Changed taste perception

Diarrhea

Nausea and vomiting

Hygiene

Food mixtures and recipes

Food supplements

Best eating habits that promotes good health

Examples of day menu’s on low budget

Further information

# MORE INFORMATION

If you are interested in the results of this project and/or you have any questions, recommendations or other useful information, do not hesitate to contact me on the following email address: cindy@aandachtvooraids.nl

Also, if you are interested in the cost estimations of this project, sponsoring or other financial backgrounds, please contact me at the above email address.